## AI Solution Map
IGEL QA AI Platform — Customer Problem → AI Solution Map
# | Customer Problem | Pain Level | AI Solution Proposed | Technology Used | When AI May Fail | How to Ensure Success | Production Status
1 | Test coverage is unknown — no visibility into which IGEL features have zero test cases | 🔴 Critical | Coverage Intelligence Engine: KG-based feature→test mapping, auto-detects uncovered features and generates missing TCs with risk scores | Knowledge Graph (PostgreSQL JSONB) + feature_coverage table + gap_reporter.py | KG extraction misses a feature if it's not clearly named in docs; new IGEL releases add features not yet in KB | Run --coverage-report after every KB ingestion; enforce doc update SOP before each IGEL release; validate KG nodes count vs. release notes feature count | 🟡 V3 Phase 8
2 | Manual test case creation is taking 6+ months with minimal progress — team is stuck writing basic TCs | 🔴 Critical | 2-Pass LLM generation: Pass 1 generates QCAPPS-format TC document; Pass 2 generates executable pytest script — both grounded in KB context, not hallucinated | Claude claude-sonnet-4-20250514 + RAG (pgvector + BM25 + RRF) + parent-child chunking | Thin KB coverage for a feature area yields hallucinated steps; rate limits slow large batches | Validate KB coverage before batch (G2 gate); run pilot 10 TCs first; use checkpoint files so batches can resume; enforce 45 RPM limit | ✅ V2 Core
3 | Generated test cases have wrong registry keys, incorrect TC Setup navigation paths — teams can't trust AI output | 🔴 Critical | Domain Accuracy Gate G4: validates every registry key against corpus, every TC Setup path against path registry, every UMS API call against IMI guide | registry_key_corpus + tc_setup_path_registry tables + corpus_extractor.py + gates.py G4 | Registry key corpus is incomplete (misses keys in older docs or images); LLM may paraphrase a path slightly differently | Build corpus from ALL KB chunks including image OCR text; use fuzzy match (edit distance ≤2); flag unmatched keys for human review — never auto-approve | 🟡 V2 Phase 3
4 | No CI/CD integration — automation scripts are not automatically validated or run in the pipeline | 🔴 Critical | TeamCity integration: KB Ingestion pipeline, TC Enrichment pipeline, Script Generation pipeline — all with checkpoint files, secure credential store, and Bitbucket PR automation | TeamCity + Bitbucket + pytest --collect-only dry-run gate (G6) + flake8 + mypy | CI environment lacks UMS sandbox for actual script execution; TeamCity secrets rotation lapses; pipeline hangs on rate limit without backoff | Set up mock UMS + IGEL device sandbox in CI; configure tenacity retry with exponential backoff; use checkpoint files for all batch runs; enforce 90-day credential rotation | 🟡 V2 Phase 4
5 | Automation scripts reference non-existent fixtures, wrong import paths, hardcoded credentials — scripts fail immediately on run | 🔴 Critical | Script Executability Gate G6: AST syntax check, import path resolver against actual framework, fixture name validator against conftest.py, credential scanner with auto-replacement | gates.py G6 + auto_repair.py + conftest.py fixture inventory + ast module | New fixtures added to conftest.py are not reflected in G6 validator until manual refresh; auto-repair substitutes wrong fixture if names are similar | G6 must reload conftest.py fixture list on every run (not cached); log every auto-repair substitution for human review; require pytest --collect-only pass in CI before PR opens | 🟡 V2 Phase 3
6 | No test prioritization — team runs all tests every release cycle, wasting time on low-risk features | 🟠 High | Risk-based prioritization via Coverage Intelligence: features with known_issues KG edges, zero existing tests, or critical registry key count score highest — generates these TCs first | knowledge_graph_edges (fixed_in, has_known_issue) + compute_risk_score() + feature_coverage table | KG 'fixed_in' edges are only as current as the last KB ingestion; risk scores don't account for customer-specific usage patterns | Ingest release notes immediately after each IGEL release; expose risk score in review dashboard; let QA lead override scores with manual priority tags | 🟡 V3 Phase 8
7 | Defect prediction is absent — team discovers failures only after test execution, not before | 🟠 High | Execution Feedback Loop: maps pytest failures back to specific TC steps → identifies patterns (wrong registry key class, missing precondition type) → generates fix suggestions and updates blacklist patterns | failure_mapper.py + kb_feedback table + analyzer.py pattern detection + G4 blacklist table | Failure mapping requires test IDs to be stable across runs; pattern detection needs >50 feedback entries to be statistically meaningful | Enforce stable TC ID naming convention from day 1; bootstrap feedback with manual entry of known-bad patterns before automated collection; run analysis cycle every 50 entries | 🟡 V3 Phase 7
8 | Context is stale — IGEL docs are updated regularly but the KB is a snapshot; generated TCs reference outdated settings | 🟠 High | Version Awareness Enforcement (Gap 5): version_tag on every chunk; G_Version gate validates generated steps against active device version; Confluence MCP fetches live release notes in real-time | version_tag column on kb_chunks + G_Version gate + Confluence MCP (live) + ingest.py version extraction | Confluence MCP is disabled until IGEL provides credentials; version regex misses non-standard version strings in docs | Activate Confluence MCP as P1 dependency; add version extraction to ingest pipeline immediately; inject active version into system prompt; flag any TC step referencing a different version | 🔴 Gap 5 — Not Started
9 | No human review workflow — QA engineers have no structured way to approve/reject AI-generated TCs before Jira push | 🟠 High | HTML Review Dashboard (G7): self-contained file per batch, shows each TC with validation badge, confidence score, KB source traceability per step, Approve/Reject/Edit buttons, batch export to approved.json | dashboard_generator.py + publisher.py (dry_run=True default) + confidence scoring formula | Reviewers may rubber-stamp without reading if dashboard is slow or confusing; export JSON may be lost before Jira push | Sort dashboard by confidence ascending (low-confidence TCs need most review); add estimated review time per TC; store approved.json in Bitbucket immediately on export; never auto-push without --no-dry-run flag | 🟡 V2 Phase 4
10 | Accuracy is unclear — no metric for how good a generated TC actually is | 🟠 High | Confidence Scoring System (Gap 1): composite score = (retrieval_score×0.3) + (validation_pass_rate×0.4) + (kb_traceability×0.3); color-coded badge in dashboard; stored in generation_runs table | confidence_score field in GeneratedTestCase + generation_runs.confidence_score FLOAT + dashboard badge | Confidence score rewards structural completeness, not semantic correctness; a TC can score 0.90 but still have a wrong navigation path | Never use confidence score as a replacement for G4 domain validation; confidence gate G_Version must pass before score is considered final; publish confidence distribution weekly for QA team review | 🔴 Gap 1 — Not Started
11 | Test acceleration is blocked — scripts take weeks to write manually; there is no path to >1000 automated tests | 🟠 High | Parallel batch generation: asyncio semaphore (max 5 concurrent LLM calls) + Redis task queue for distributed workers + checkpoint files for resumable runs + 45 RPM rate limiting | asyncio.Semaphore + tenacity retry + rq workers (Redis optional) + batch_checkpoint.json | Azure OpenAI rate limits cause silent failures without retry; Redis not available in all environments; checkpoint corruption on force-kill | Implement tenacity exponential backoff on every LLM call; default to asyncio.Queue (no Redis needed for <500 TCs); write checkpoint atomically using temp file + rename; enforce max 50 TCs per batch CLI invocation | 🔴 Gap 7 — Not Started
12 | Duplicate test cases — team generates TCs for the same feature multiple times without knowing | 🟡 Medium | Pre-generation duplicate check (Improvement B): embed topic, compare cosine similarity against generation_runs.topic_embedding, block at >0.92 similarity unless --force-duplicate flag used | generation_runs.topic_embedding VECTOR(3072) + cosine similarity check before Pass 1 LLM call | Semantic similarity threshold too tight misses near-duplicates with different wording; too loose blocks valid new TCs for updated feature versions | Default threshold 0.92 (tunable); always show the existing TC path when blocking; 'Possible Duplicate' badge at >0.85 in dashboard without blocking; re-run similarity after major KB updates | 🔴 Improvement B — Not Started
13 | Knowledge relationships are invisible — team doesn't know which features depend on each other or share registry keys | 🟡 Medium | Knowledge Graph Layer: extracts Feature→RegistryKey, Feature→UIPath, Feature→depends_on relationships; enables multi-hop queries (e.g., 'what features use this SSO provider?'); reduces hallucination by providing structured facts | knowledge_graph_nodes + knowledge_graph_edges tables + KGExtractor (GPT-4.1) + KGRetriever 1–2 hop expansion | KG extraction via LLM can hallucinate relationships; low-confidence edges pollute retrieval context | KG Validator (Gap 4): every entity must appear verbatim in source chunk; edge confidence scored by co-occurrence proximity; only use edges with confidence ≥0.5 in retrieval; bulk-validate KG after build | 🟡 V3 Phase 5
14 | Retrieval quality is opaque — team cannot tell why a TC was generated with wrong context | 🟡 Medium | Retrieval Debug Visibility (Gap 3): every SearchResult carries vector_score, fts_score, rrf_score, rerank_score; dashboard shows expandable Retrieval Debug panel per TC with source file, section title, all scores | SearchResult dataclass extensions + retrieval_debug.json per TC + dashboard debug panel | Debug panel adds cognitive load to review dashboard; storing full retrieval trace per TC increases disk usage significantly at scale | Make debug panel collapsed by default (expand on click); store retrieval debug JSON only for flagged/low-confidence TCs to cap disk use; provide weekly retrieval quality report summarizing average RRF scores by product | 🔴 Gap 3 — Not Started
15 | Images in IGEL docs are ignored — configuration dialogs, UI screenshots, registry trees are not used in TC generation | 🟡 Medium | Image Intelligence Pipeline: extract images from PDF/DOCX → filter recurring/decorative → Claude Vision API → structured JSON (image_type, verbatim_text, ui_elements[], test_relevance) → embed + store in kb_images | Claude Vision API + PyMuPDF + SHA-256 deduplication + kb_images table with description_embedding | Vision API misclassifies diagram type; 'test_relevance' field is too vague for step generation; high-frequency recurring images (headers) not filtered if frequency threshold is wrong | Validate Vision output with IGEL relevance filter (skip if test_relevance starts with 'Reference image only' AND verbatim_text is empty); set recurring image threshold to 25% of document pages; manually audit first 50 image descriptions | ✅ V2 Core
16 | Feedback is collected but never used — human corrections and execution failures don't improve future generation | 🟡 Medium | Closed Feedback Loop (Gap 6): analyzer.py publishes retrieval boost list (chunk_id→boost_weight), prompt patch file (recurring error patterns → 'Do NOT' rules), blacklist patterns table — all automatically applied in next generation run | kb_feedback_boosts table + prompts_patches.json + kb_feedback_blacklist table + feedback/scheduler.py | Boost weights amplify biases if feedback sample is small; prompt patches may conflict with each other after many cycles; blacklist may over-restrict valid but rare patterns | Require minimum 20 feedback entries before activating boost list; cap prompt patches at 10 active rules (retire oldest when adding new); expose boost list and patches to QA lead for manual review before activation | 🔴 Gap 6 — Not Started

## Production Gaps Tracker
IGEL AI Platform — Production Readiness Gap Tracker (V2 + V3)
Gap ID | Gap Title | Severity | V2 or V3 | Affected Phase(s) | What Happens Without It | Implementation File(s) | Effort (Days) | Priority
Gap 1 | No Confidence Scoring System | 🔴 Critical | V2 | Phase 3, 4 | All gates are binary pass/fail — reviewer cannot prioritize which TCs need most attention; no auto-approval path ever exists | gates.py + generation_runs table + dashboard_generator.py | 3 | P1 — Block Review
Gap 2 | Missing Step-Level Traceability | 🔴 Critical | V2 | Phase 2, 4 | No audit trail for which KB chunk backs each step — untrustworthy for enterprise sign-off; cannot debug wrong steps efficiently | test_generator.py (Pass 1 prompt) + validation.json + dashboard_generator.py | 4 | P1 — Block Audit
Gap 3 | No Retrieval Debug Visibility | 🟠 High | V2 | Phase 2, 4 | Cannot tune retrieval without seeing why chunks were selected; silent quality degradation goes undetected | retriever.py SearchResult dataclass + retrieval_debug.json + dashboard panel | 2 | P2 — Tuning
Gap 4 | KG Extraction Hallucination Risk | 🔴 Critical | V3 | Phase 5 | Knowledge Graph contains phantom entities and invented relationships — poisons all KG-augmented generation with wrong facts | knowledge_graph/validator.py + KGExtractor validation hook + confidence column on edges | 3 | P1 — Block KG
Gap 5 | No Version Awareness Enforcement | 🔴 Critical | V2+V3 | Phase 1, 2, 3 | TCs generated for IGEL OS 12.8 may contain steps valid only in 12.3 — test fails in production lab without explaining why | kb_chunks.version_tag + retriever.py version_filter + G_Version gate + prompts.py version injection | 4 | P1 — Block Accuracy
Gap 6 | Feedback Loop Not Closed | 🟠 High | V3 | Phase 7 | Human corrections and execution failures are stored but never applied — same errors repeat indefinitely; system never improves | feedback/analyzer.py + kb_feedback_boosts table + prompts_patches.json + kb_feedback_blacklist | 5 | P2 — Long-term
Gap 7 | Parallelism and Scaling Undefined | 🟠 High | V2 | Phase 4 | batch_generate() has no concurrency limit — simultaneous Azure OpenAI calls trigger rate limits; no checkpoint = lost work on failure; no path to 14K TCs | test_generator.py batch_generate() + asyncio.Semaphore + tenacity retry + checkpoint file | 3 | P1 — Block Scale
Imp A | Query + Embedding Cache Missing | 🟡 Medium | V2 | Phase 2 | Repeated queries to same topic re-embed and re-retrieve every time — wastes ~30% API cost; slow interactive generation | utils/cache.py (diskcache) + azure_embedder.py cache check + retriever.py cache layer | 2 | P3 — Cost
Imp B | No Pre-generation Duplicate Check | 🟡 Medium | V2 | Phase 4 | Team generates TCs for same feature area repeatedly — review queue fills with near-identical content; wasted review time | generation_runs.topic_embedding VECTOR(3072) + similarity check in test_generator.py | 2 | P3 — Quality
Imp C | Binary Pass/Fail — No Failure Classification | 🟡 Medium | V2 | Phase 3, 4 | When a TC fails validation, team must manually read the gate output to understand why — no triage signal for CI/CD reporting | gates.py ValidationResult.failure_class enum + dashboard filter + gap_reporter failure distribution | 1 | P3 — DX
Ops 1 | No Context Freshness SOP | 🔴 Critical | Ops | All phases | KB becomes stale within weeks of each IGEL release — generated TCs reference deprecated settings; team discovers this during execution, not generation | SOP document + ingest.py scheduled run + Confluence MCP activation + IGEL doc update notification process | 2 | P1 — Block Ops
Ops 2 | No KB Coverage Completeness Metric | 🟠 High | Ops | Phase 1, 8 | Cannot answer: 'Does our KB cover 100% of IGEL OS 12 features?' — blind spots in KB = blind spots in test coverage | coverage_engine.py + feature_coverage table + gap_reporter.py + weekly coverage dashboard | 3 | P2 — Visibility
Ops 3 | Jira / Confluence Access Not Granted | 🔴 Critical | Ops | Phase 2, 10 | Jira MCP and Confluence MCP are wired but disabled — losing live format examples, feature tickets, and real-time release notes | IGEL IT action: provide JIRA_API_TOKEN, CONFLUENCE_API_TOKEN, CONFLUENCE_SPACE_KEY | 0 | P1 — IGEL Action
Ops 4 | No TeamCity Monitoring / Alerting | 🟠 High | Ops | Phase 4 | Batch run failures (rate limit, DB timeout, checkpoint corruption) go undetected until someone manually checks the build log | Structured JSON logging + Prometheus metrics export + Slack webhook on pipeline failure + TeamCity email alert config | 2 | P2 — Ops

## Implementation Roadmap
IGEL AI Platform — Phased Implementation Roadmap (V2 + V3 + Gaps)
Milestone | Phase | Deliverables | Files Created / Modified | Dependencies | Verification Step | Effort | Target Week | Gate Activated | Status
M1 | V2 Ph1 | Schema extensions (6 tables): registry_key_corpus, tc_setup_path_registry, ums_api_corpus, generation_runs, kb_feedback, version_tag columns | schema.py (6 table additions), migration script | Existing schema.py, db/client.py | psql: \d+ registry_key_corpus shows > 0 rows after --build-all run | 3d | Wk 1 | — | 🔴 Not Started
M2 | V2 Ph1 | Corpus extractor: registry keys, TC Setup paths, UMS API endpoints extracted from all KB chunks | validation/corpus_extractor.py + CLI --build-all | M1 schema tables | registry_key_corpus has >50 rows; tc_setup_path_registry has >20 rows; verified by QA lead | 2d | Wk 1 | G4 prerequisite | 🔴 Not Started
M3 | V2 Ph2 | G1–G3 + G5 gates: ingestion integrity, retrieval relevance, schema compliance, step completeness with auto-repair | validation/gates.py, validation/auto_repair.py | M1+M2, existing retriever.py + test_generator.py | Inject bad schema TC → G3 fires and auto-repairs; inject low-RRF topic → G2 widens search | 4d | Wk 2 | G1, G2, G3, G5 | 🔴 Not Started
M4 | V2 Ph2 | Confidence scoring + step-level traceability (Gap 1+2): [SOURCE:chunk_id] tags in generation, kb_traceability metric, confidence_score field | test_generator.py (Pass 1 prompt) + gates.py + validation.json format | M3 gates framework | Generated TC validation.json shows step_sources array with ≥80% steps having a chunk_id | 3d | Wk 2 | Confidence score | 🔴 Not Started
M5 | V2 Ph3 | G4 Domain Accuracy + G6 Script Executability + auto_repair.py full implementation | validation/gates.py (G4, G6), validation/auto_repair.py | M2 corpus tables, M3 gate framework | Inject fake key app.zoom.fake.key → G4 flags with nearest suggestion; inject broken import → G6 auto-repairs | 4d | Wk 3 | G4, G6 | 🔴 Not Started
M6 | V2 Ph3 | Version Awareness Enforcement (Gap 5): version_tag column, G_Version gate, version injection in prompts | schema.py (version_tag), retriever.py (version_filter), gates.py (G_Version), prompts.py | M1 schema, M3 gates | TC generated for OS 12.8 config does not reference OS 12.3-only settings; G_Version fires on version mismatch | 3d | Wk 3 | G_Version | 🔴 Not Started
M7 | V2 Ph4 | Parallelism + scaling (Gap 7): asyncio semaphore, tenacity retry, checkpoint file, batch size limit | test_generator.py batch_generate(), generate.py CLI | M5+M6 | Kill batch mid-run → resume from checkpoint, 0 re-generated TCs; 5 concurrent calls sustained without rate-limit errors | 3d | Wk 4 | Scale gate | 🔴 Not Started
M8 | V2 Ph4 | HTML Review Dashboard (G7) + publisher.py (dry_run=True default) + ValidationPipeline orchestration | review/dashboard_generator.py, review/publisher.py, validation/pipeline.py | M3–M7 gates, existing generate.py | Open batch_review.html: all TCs show confidence badge, registry key validation status, KB source per step, Approve/Reject buttons functional | 4d | Wk 4–5 | G7 | 🔴 Not Started
M9 | V2 Ph4 | TeamCity pipeline configs: KB Ingestion, TC Enrichment, Script Generation + Bitbucket PR automation | teamcity/igel_kb_ingestion.xml, teamcity/igel_tc_enrichment.xml, teamcity/igel_script_gen.xml | M8 complete, TeamCity + Bitbucket access | Trigger TC enrichment build → runs 10 pilot TCs → outputs review HTML → PR opened with generated scripts | 3d | Wk 5 | CI/CD | 🔴 Not Started
M10 | V3 Ph5 | KG Foundation: knowledge_graph_nodes + edges tables + KGExtractor (GPT-4.1) + KGValidator (Gap 4) + KGRetriever | knowledge_graph/extractor.py, knowledge_graph/validator.py, knowledge_graph/retriever.py | M1 schema pattern, existing ingest.py | knowledge_graph_nodes has >100 entries; all edges have confidence ≥0.5; phantom entity test (entity not in source chunk) correctly rejected | 5d | Wk 6–7 | KG prerequisite | 🔴 Not Started
M11 | V3 Ph6 | Cross-encoder reranking + Context Fusion Engine (RAG + KG combined context window) | retriever.py (rerank option), fusion/context_fusion.py, prompts.py (fused context builder) | M10 KG complete | Generation with --rerank shows KNOWLEDGE GRAPH CONTEXT section in prompt log; retrieval quality improves vs. baseline (measure RRF score distribution) | 4d | Wk 7–8 | Rerank, Fusion | 🔴 Not Started
M12 | V3 Ph7 | Execution Feedback Loop: failure_mapper, collector, analyzer — kb_feedback table fully wired | feedback/collector.py, feedback/analyzer.py, feedback/failure_mapper.py, feedback/scheduler.py | M8 dashboard, M1 schema | Record mock failure → kb_feedback entry created; after 20 entries → analyze_patterns() returns classification; boost list created | 4d | Wk 8–9 | Feedback | 🔴 Not Started
M13 | V3 Ph7 | Closed Feedback Loop (Gap 6): boost list → retrieval weighting, prompt patches, blacklist patterns all auto-applied | retriever.py (boost loading), prompts.py (patch injection), kb_feedback_blacklist table | M12 feedback collector | After 20+ feedback entries: retriever loads boost list on init; system prompt includes active patches; G4 checks blacklist | 3d | Wk 9 | Feedback closed | 🔴 Not Started
M14 | V3 Ph8 | Coverage Intelligence Engine: feature→test map, gap detection, duplicate detection, risk scoring, gap report | coverage/coverage_engine.py, coverage/gap_reporter.py | M10 KG, M8 generation_runs table | Run --coverage-report --product 'IGEL OS' → markdown report shows uncovered features list, near-duplicate TCs, risk-ranked backlog | 4d | Wk 10 | Coverage | 🔴 Not Started
M15 | Ops | Context Freshness SOP + Confluence MCP activation + KB completeness metric | SOP document + confluence_mcp.py activation + coverage dashboard | IGEL Confluence credentials (P1 action from IGEL IT) | KB ingestion runs within 48h of each IGEL release; Confluence MCP returns live TC Setup paths for current release | 2d | Wk 10+ | Ops | 🔴 Blocked: IGEL IT

## Current State Audit
IGEL AI Platform — Current State Audit: Implemented vs. Missing
Component | Module / File | Status | What's Working | What's Missing | Action Required
Ingestion Pipeline | ingest.py + parsers | ✅ Implemented | PDF/DOCX/CSV/MD parsers, hierarchical chunking (parent+child), dedup, Azure embeddings (3072-dim), pgvector schema (5 tables), image intelligence pipeline | Version tag extraction not wired; corpus extractor (registry keys, TC Setup paths) not called post-ingestion; KG extraction not wired | Add version_tag to kb_chunks; call corpus_extractor.build_all() and KGExtractor after each file ingestion
Embedding Model | azure_embedder.py | ✅ Implemented | text-embedding-3-large (3072-dim) working; embeds both text chunks and image descriptions | No embedding cache — every run re-embeds queries; no cache invalidation strategy | Implement QueryCache with diskcache (Improvement A); add SHA256 cache key per text; 24h TTL
Hybrid Retrieval | retriever.py | ✅ Implemented | pgvector cosine search + BM25 tsvector + RRF fusion (k=60); dedup by parent_chunk_id; image context inline | No cross-encoder reranking (Phase 6); no G2 gate wired in; no retrieval debug scores captured; no version_filter; no feedback boost loading | Add rerank=True option; wire G2 gate; capture vector_score/fts_score/rrf_score per result; add version_filter param
Image Intelligence | kb_images table + Vision pipeline | ✅ Implemented | Extract from PDF/DOCX, filter recurring images (SHA-256 + frequency), Claude Vision JSON output (image_type, verbatim_text, ui_elements, test_relevance), embed + store | Image descriptions not used in traceability mapping; no validation that Vision output is correct; image OCR not feeding into registry key corpus | Wire kb_images into corpus_extractor for registry key and path extraction; add image accuracy sample audit
MCP Adapters | PostgresMCP, JiraMCP, ConfluenceMCP | ⚠️ Partial | PostgresMCP fully active. JiraMCP and ConfluenceMCP fully written and wired | JiraMCP disabled (JIRA_ENABLED=false) — missing IGEL Jira credentials. ConfluenceMCP disabled — missing IGEL Confluence credentials | IGEL IT to provide: JIRA_BASE_URL, JIRA_USER_EMAIL, JIRA_API_TOKEN, CONFLUENCE_BASE_URL, CONFLUENCE_API_TOKEN, CONFLUENCE_SPACE_KEY
Test Generation | test_generator.py (2-pass) | ✅ Implemented | Pass 1: QCAPPS-format markdown TC from KB context. Pass 2: executable pytest script. IGEL expert system prompt with context-only rule | No [SOURCE:chunk_id] tags in Pass 1 prompt; no version injection; no G3/G5 validation wired in; no duplicate check before Pass 1; no batch concurrency limit | Add source tag instruction to Pass 1 prompt; inject device_version from config; wire ValidationPipeline; add duplicate check; add semaphore limit
Validation Gates | validation/gates.py | ❌ Not Started | Nothing yet | G1 (ingestion integrity), G2 (retrieval relevance), G3 (schema compliance), G4 (domain accuracy), G5 (step completeness), G6 (script executability), G7 (human review), G_Version — all missing | Implement gates.py, auto_repair.py, pipeline.py as highest priority before any production use
Domain Corpus | registry_key_corpus, path_registry | ❌ Not Started | Nothing yet | registry_key_corpus table not created; tc_setup_path_registry not created; corpus_extractor.py not written; G4 gate has nothing to validate against | M1+M2 in roadmap: create tables, write corpus_extractor.py, run --build-all, validate with QA lead before G4 activation
Confidence Scoring | generation_runs.confidence_score | ❌ Not Started | Nothing yet | No confidence_score field; no retrieval_score/validation_pass_rate/kb_traceability sub-scores; no dashboard badge | Implement as part of M4 (Gap 1); required before dashboard is useful for prioritization
HTML Review Dashboard | review/dashboard_generator.py | ❌ Not Started | Nothing yet | No human approval workflow; no validation status display; no KB source traceability view; no batch export to approved.json | M8 in roadmap: highest-priority UX deliverable; blocks all Jira push workflows
Knowledge Graph | knowledge_graph/extractor.py + retriever.py | ❌ Not Started | Nothing yet | No entity/relationship extraction; no KG nodes/edges tables; no KGValidator; no 1-2 hop expansion in retrieval; no Context Fusion Engine | M10–M11 in roadmap (V3); prerequisite: all V2 gates stable first; KGValidator (Gap 4) must be implemented before KG goes to production
Feedback System | feedback/ module | ❌ Not Started | Nothing yet | kb_feedback table not created; no failure_mapper; no analyzer; feedback loop not closed (Gap 6) | M12–M13 in roadmap (V3 Phase 7); do not implement before 200+ TCs have been reviewed (need feedback volume)
Coverage Intelligence | coverage/coverage_engine.py | ❌ Not Started | Nothing yet | feature_coverage table not created; no feature→test map; no gap report; no risk scoring | M14 in roadmap (V3 Phase 8); requires KG (M10) and generation_runs table (M1)
CI/CD Integration | TeamCity + Bitbucket pipelines | ❌ Not Started | Nothing yet | No TeamCity build configs; no Bitbucket PR automation; no secure credential store for API keys; no monitoring/alerting | M9 in roadmap (V2 Phase 4); requires M8 dashboard complete; set up mock UMS sandbox in CI for script dry-run
Parallelism/Scale | batch_generate() + asyncio + Redis | ❌ Not Started | Nothing yet | Sequential generation only; no semaphore; no checkpoint file; no tenacity retry; no rate limit enforcement | Gap 7 / M7 in roadmap: implement before any batch >50 TCs; asyncio.Queue default (no Redis needed initially)

## Context Freshness SOP
IGEL AI Platform — Context Freshness & Knowledge Base Update SOP
Trigger Event | Who Owns It | Action Required | Files / Systems | SLA | Impact if Missed | Automation Possible?
New IGEL OS release (e.g. OS 12.9) | IGEL QA Lead | 1. Download all updated PDFs from IGEL portal. 2. Run ingest.py --rebuild for new docs. 3. Run --build-all corpus extractor. 4. Run KG extractor. 5. Validate coverage report. | ingest.py, corpus_extractor.py, KG extractor, coverage_engine.py | Within 48h of release | Generated TCs reference deprecated settings; G4 corpus misses new registry keys; coverage gaps remain invisible | ✅ Automate: Confluence MCP fetches release notes; ingest pipeline triggered by doc commit to Bitbucket
New IGEL App version (Zoom, Citrix, Teams, etc.) | App QA Owner | 1. Download updated Apps guide PDF. 2. Re-ingest this document only (not full rebuild). 3. Run selective corpus extraction for affected product. 4. Check G2 retrieval scores for app-related queries. | ingest.py --file <app_guide.pdf>, corpus_extractor.py --product APPS | Within 24h of app release | App-specific TCs use outdated navigation paths and missing new registry keys | ✅ Automate: Confluence MCP + Jira APPS-* ticket feed
IGEL UMS version update | UMS QA Owner | 1. Re-ingest UMS administrator guide. 2. Update ums_api_corpus from new IMI guide if API changed. 3. Flag existing TCs that reference deprecated UMS API endpoints in G4. | ingest.py, corpus_extractor.py --build-ums-api, gates.py G4 API validator | Within 48h of UMS release | UMS API port, endpoint paths, or response formats may have changed — scripts fail silently | ⚠️ Partial: manual download needed; ingest + corpus update automatable
New registry key discovered in defect report | QA Engineer (defect triage) | 1. Add registry key manually to registry_key_corpus via CLI or direct DB insert. 2. Add source reference. 3. Re-run G4 validation on any affected TCs. | registry_key_corpus table INSERT, corpus_extractor.py --add-key CLI | Within 1 business day | G4 validator flags the key as unknown on next generation run — routes to human review unnecessarily | ✅ Automate: G4 rejection → prompt QA engineer to add to corpus via dashboard action
TC Setup path changes in new OS version | IGEL QA Lead | 1. Identify changed paths from release notes. 2. Update tc_setup_path_registry via CLI or direct DB. 3. Add deprecation flag to old paths. 4. Re-validate affected TCs. | tc_setup_path_registry table UPDATE + version_introduced column | Within 48h of release | G4 path validator either passes wrong path (if registry not updated) or blocks valid path (if old entry not deprecated) | ⚠️ Partial: Confluence MCP can detect path changes; registry update still needs human confirmation
Quarterly KB completeness audit | QA Architecture Lead | 1. Run --coverage-report for all products. 2. Review uncovered feature list. 3. Identify KB gaps (features in IGEL docs not in KB). 4. Prioritize missing docs for ingestion. 5. Update knowledge_graph_nodes with manually confirmed entities. | coverage_engine.py --all-products, gap_reporter.py, knowledge_graph_nodes manual review | Quarterly | Systematic blind spots in coverage go undetected; risk-based prioritization scores are incorrect | ✅ Automate: scheduled quarterly report email to QA Lead
Human correction in review dashboard | QA Reviewer | 1. Correction is auto-captured in kb_feedback table when reviewer edits and approves. 2. After 20+ corrections: run feedback analyzer. 3. Review boost list and prompt patches before activation. | feedback/collector.py, kb_feedback table, feedback/scheduler.py, prompts_patches.json | Analyzer runs every 50 feedback entries | Corrections are stored but never applied — same errors repeat; team loses trust in AI output | ✅ Automate: feedback/scheduler.py triggered every 50 entries via cron or TeamCity
Jira APPS-* new feature ticket | Product QA (when Jira MCP active) | 1. JiraMCP polls new APPS-* tickets on generation request. 2. New Features and Known Issues sections auto-populated in TC document. 3. No manual action needed. | JiraMCP (activate with JIRA_ENABLED=true when credentials available) | Real-time on generation | New features and known issues missing from TC document — reviewer must manually add JIRA references | ✅ Fully automatic once IGEL provides Jira credentials